Hilton – 24Oct23 meeting

# Proposed Agenda

1. Outreach
   1. Advisory board meeting
2. Harmonization
3. Analysis
   1. Submitted papers
   2. Domestic violence
   3. Pre-primary
   4. Education implementation
   5. Methodology-focused paper

Paper Tracking

* Edu & edu outcomes – submitted to International Journal of Education Research – October 5
* CM & edu – submitted to Child Services – August 23
* Edu & ANC – submitted to BMC Pregnancy and Childbirth – August 4
* DV & wasting – submitted to PLoSOne – July 26
* Edu & wasting – submitted Global Public Health – response to reviewers submitted – October 4

Deliverable Tracking

**Year 3**

* *No longitudinal policy data and harmonization data goals*
* Long-term impact of ECD policies on all key outcomes in adulthood conducted
* Evidence from 1.3; data made available
* 6 (1 global; 5 country) country toolkits. A summary policy brief that ties together the research evidence to build a compelling invest case will complement these toolkits. By project end, a comprehensive global repository for learning about the impact of expanding ECD policies on outcomes will be in place.
* 3 advisory board meetings
  + November 7
* 1 Global launch event with 15 – 20 highly engaged stakeholders from civil society, research and policy sectors
  + Targeting August meeting
  + 6 launch events from April - September
* 5 UN reports submitted
* Documented use of research findings by key stakeholders